Projects: temporary; have definite start and end dates; produce a unique product, service, or result;

- Projects are completed when one of these are met:

- Goals and objectives have been met and signed off by the stakeholders

- Terminated because the goals and objectives cannot be accomplished.

- Canceled because no longer needed.

- Ongoing operations do not have a beginning or an ending date.

- Project management is applying tools, techniques, skills, and knowledge to project activities and it involves roles, responsibility, and authority levels to bring successful results and meet the project requirements.

- Programs are groups of related projects, subprograms, or other works that are managed using similar techniques in a coordinated fashion. It be should done only when the program approach adds value.

- This may achieve decreased risk, Economies of scale, and improved management.

- Portfolios are collections of programs, sub portfolios, operations, and projects that support strategic business goals or objectives and may not be related to each other’s.

- This may achieve optimize the use of resources, enhance the benefits to the organizing and reduce risk.

Organizational Project Management (OPM) is a strategy execution framework utilizing project, program, and portfolio management as well as organizational enabling practices to consistently and predictably deliver organizational strategy producing better performance, better results, and a sustainable competitive advantage. It is a framework for keeping all focused on the overall strategy.

It provides direction to prioritize managed, executed and measured to best achieve the strategic goals.

Management By objectives (MBO): A management system in which the objectives of an organization are agreed upon so that management and employees understand a common way forward. And must be supported by management.

Governance: used in the industry describes the processes that need to exist for a successful project and it met the strategically goals. It works best when standards are selected and enforced across projects and programs within a portfolio or organization.

OPM3: it is a PMI Organizational Project management maturity model.

PMO is to provide support for project managers:

- Supportive: provide the polices , mythologies and it is a template project repository - LOW

- Controlling: provide support and guidance and trains and ensure projects compliances- MED

- Directive: Director and mange PMs and it responsible for the result of those projects- HIGH

PMO can exist in all organizational structures. It might called project offices or program management offices or Centers of Excellence. The establishment of a PMO is not required in order for you to apply good project management practices to your next project

And for establish the PMO is must defined the role of PMO and defined its standards.

Stakeholders have something to either gain or lose as a result of the project and you should continue to ask fellow team members and stakeholders if there are other stakeholders who should be a part of the project.

When in doubt, you should always resolve stakeholder conflicts in favor of the customer

A project manager within a functional organization has little to no formal authority and Authority rests with the VP. Their title might not be project manager; instead, they might be called a project leader, a project coordinator, or perhaps a project expeditor.

Functional Organizations is the oldest style of organization and the traditional approach to organizing businesses.

Each department or group in a functional organization is managed independently and has a limited span of control.

Workers in functional organizations specialize in an area of expertise

One of the keys to determining the type of organization you work in is measuring how much authority senior management is willing to delegate to project managers

In functional organization, the vice president or senior department manager is usually the one responsible for projects

The idea behind a projectized organization is to develop loyalty to the project, not to a functional manager

PM in projectized organization have the authority to choose and assign resources from other areas in the organization or to hire them from outside if needed.

PM authority not related to key stockholders.

The primary competing demands on projects are scope, schedule, cost, risk, resources, and quality.

Co-located, which means team members. Tight matrix (colocation): locating a space for team members.

One obvious drawback to a projectized organization is that project team members might find themselves out of work at the end of the project

In Matrix organizations, the functional manager is the one in charge of assigning or freeing up resources to work on projects

In Matrix organizations, the project manager simply expedites the project

In functional the key of success are Networking and leadership.

The balanced matrix is exactly that—a balance between weak and strong, where the project manager shares authority and responsibility with the functional manager

Project-based organizations (PBOs) refer to various organizational forms that create temporary systems for carrying out their work.

PBOs can be created by different types of organizations (functional, matrix or Projectized)

The use of PBOs may diminish the hierarchy and bureaucracy inside the organizations as

The success of the work is measured by the final result rather than by position or politics.

Enterprise environmental factors: (Baggage) : are internal or external factors that can influence a project’s success and PM will have deal with such as:

-	Organizational culture and structure

-	Internal and external political climate

-	Existing human resources and available capital resources

-	Regulatory environment

-	Financial and market conditions

- 	Existing system that the like type of the organization, which it and it can be

Project comply with organization strategy is obtain the support through performing

Project Management Information system (PMIS): is part of Enterprise environmental factors and it include automated tools, software, repositories for historical information. And a Change control system and also have Configuration Management system and also contains a Work authorization system

Organizational Process Assets: include any of the organization’s process assets that may be used to ensure project success. Like:

- Processes, guidelines, and procedures, such as: organizational standard processes, standardized guidelines, templates

- The corporate knowledge base, such as, lessons learned, historical information, past project files (I call this: The Repository of Goodness)

Cooperate Knowledge Base: an indexed records information; historical information and lessons learned.

Historical information: is a record of past projects used to manage the future projects such as activates risks lessons learned resources used.

Lesson learned written by the stockholders.

Work Performance Date: initial measurement and details about activities gathered during the project work “Executing”: the design took 10 days and completed in 21 june

Work Performance Information: is an analyzing of Work Performance Date to make sure they conform the plan. It suppose the design take 9 days why this happen and what we need to do.

Work Performance Reports: is the organized Work Performance Information reported to stakeholders.

Project Life Cycle: there are many of them

Plan-Driven:

Predictive Cycles (Fully Plan-Driven Approach, Waterfall, or traditional life cycle): The work of each phase is usually distinct and not repeated in other phases. The cost schedule and scope are determined in detail early.

Change-driven are a perfect choice for large projects, complex projects.

Iterative: early planning of high level with a prototype then iterative it.

Incremental: early planning of high level with full function then increment it.

Adaptive:  fixed time and cost. The scope is broadly defined and it will redefined.

Projects …P48 to explain the whole process.

Scope creep: uncontrolled change

All the work of the Project and project management MUST be monitored and controlled.

Determine the role and responsibility is involving determining who required to provide reports. And Who will attend meetings , who will work with Quality department etc..

We can release the team member when his work are completed in any time of project life.

Changes can be requested during Executing AND M&C.

The Project Process Group DOESNOT occur sequentially they all OVERLAP.

In initiating the PM provided with the authority and Information he need.

The Output of the initiate group are:

Project charter

Stakeholder’s registry

The Initiating process involves many things:

- Assign the project manager

- Defined a high-level requirement, risks….

- …

- P 71

Progressive elaboration: in general, means developing something in incremental steps even after you have an approved final project plan and the project starts executing, progressive elaboration continues to some extent and the projects are progressively elaborated into more and more detail over time until they are complete and finalized. It is often used when creating the project or product scope, developing requirements, determining human resources, scheduling, and defining risks and their mitigation plans

When to enter the initiate process:

Business need, Begin new phase and Project has many problem and need to reevaluate

In planning the PM and his team determine which KA Process they need for the project to avoid wasting resource. The project manager and project team are responsible for determining which processes within each process group are appropriate for the project on which you’re working. This is called tailoring

Rolling wave Planning: detailed planning for the next phase is done as previous phase nears completion or when start the phase but the high level plan must be exist.

Everyone is involved in Planning

When to enter the Planning process:  Project Initiation in completed.

When to enter the Executing process: Project Planning in completed OR Integrated change control results in change

After Risk analysis the final cost and schedule will be finalize.

Try to make up the deviation before request a change Make it the LAST RESORT and used it there is NO other way to make up the deviation.

When to enter the M&C process:

- Requested a change

- Work Performance data

- Deliverables

The output are

- To Project initiate to review the project charter

- To Execution to make an approved change

- To Closing

In Closing you must Celebrate and send thanks !! and also an acceptance and measure the customer satisfaction.

Handoffs (technical transfers): Project phases evolve through the life cycle in a series of phase sequences.

Phase end reviews are also known by a few other names: phase exits, phase gates, phase reviews, milestones, stage gates, and kill points.

Sequential Relationships one phase must finish before the next phase can begin.

Overlapping Relationships one phase starts before the prior phase completes

Sometimes phases are overlapped to shorten or compress the project schedule. This called fast tracking

When the project initiated, costs are low and few team members assigned to the project but Risk is highest and Stakeholders influencing at the beginning of the project and gradually decreases the closer the project comes to completion

The greatest conflicts a project manager will encounter in process group ”Planning” are project prioritization issues

The group of people conducting the feasibility study should not be the same people who will work on the project.

A steering committee is a group of folks consisting of senior managers and sometimes mid-level managers who represent each of the functional areas in the organization

Product life cycle : after the project life cycle finish the product move to operation.

The Project Manager main role is to perform integration management.

To create Project Charter: it may useful to meet key stakeholder to identify the high level project objective, constrains, scope, risk and assumptions in an effort to assess the feasibility of the project.

Details plans need time and money, which needs approve the project charter.

The project officially authorized when the project charter is signed.

It gives the PM authority to spend money commit cooperate resources to the project.

The project is not a project until the project charter is approved, and the project charter cannot be started until the business case is approved

There are some factors influence creating the Project charter:

- Business Case.

- Project selection

- Constrains and assumptions

- SOW

- Agreements/contracts

- Any relevant organizational process assets(process, templates, historical ,lessons learned)

Business Case captures the business need and it explain why the project was selected. How it fit into organization strategic goals and how it will bring business value to the organization.

There are two categories of project selection

- Benefit measurement methods (comparative approach)

    - Murder board

    - Peer view

    - Scoring models

    - Economic models

- Constrained optimization methods (mathematical approach)

    - Liner programming

    - Integer programming

    - Dynamic programing

    - Multi-objective programing

Law of Diminishing Return :

Deprecation:

- Straight line of deprecation:

- Accelerated Deprecation :double decline balance , sum of years

Constrains are factors that limit the team’s option.

Project statement of work  is created by the customer or sponsor and describes their needs.

If we received as an input to develop the project charter.

Management plan is unique for every project.

Even if there is not an execution plan for a process the work performance data related to the knowledge area still needs to be gathered as part of Direct and Manage Project Work.

Project Management Plan include:

- Project management process will be used in the project (Tailoring)

- KA management plans:

- Scope, schedule and cost Baseline: Baselines used to compare the actual performance against the planed performance.(together they are called Performance measurement baseline)

- Requirements management: plan how requirement (stakeholder needs, wants, expectation… ) , will be gathered, analyzed ,prioritized and how it will be managed

- Change Management plan: manage change and the change process on the project.

- Configuration management plan: managing changes to the documentation about the deliverables and process of the project.

- Process improvement plan : define how processes that are used on the project to complete the work will be evaluated and improved

If the project deviates from the baseline, you need to review the risk management plan.

The Project Management plan must be signed from the team, sponsor and key stakeholder.

Project document: any project-related document not part of management plan such as project charter, SOW, agreements, contracts etc...

The updates of Project document are output of many project processes.

Kickoff meeting before the end of planning.

In Direct and manage project work:

- Integrate all the executing work into one effort.

- Involves gathering work performance data

- Requesting changes

- Completing the approved change requests.

The input of Direct and manage project work are:

- Projects plans

- Approved changed, corrective actions preventive actions and defect repair

The output:

- New change request

- Deliverables

- Work performance data

- Implement approved changed, corrective actions preventive actions and defect repair

- Update to the Projects management plan and project document

Work authorization system is for authorizing the start of work package or activity.

Corrective action deals with actual deviations.

Preventive action like train member, replace one because he failed in last activity

Not all requested changes must be done.

To perform the Integrated change control it must be for something has been issued and finalized if it is still in the process no need to go through the Integrated change control

Change Control Board: responsible for reviewing and analyzing change requests in accordance with change management plan for the project.

Process of making changes:

- Evaluate the impact.

- Identify options

- Get the change request approval internally

- Get customer buy in.

Scope Management it the process of defining what work is required and then making sure all of the work and only that work is done.

Gold plating a project is not allowed.

Changes not related to project charter should not be approved.

Creating WBS is required.

The output of plan scope management are:

- Scope management plan

- Requirement management plan

Miss a requirement could mean project failure.

The requirement are collected from the stakeholder recorded in stakeholder register through any techniques such as:

- Reviewing Historical Records.

- Interviews “expert interview”,

- Focus Group: selected group from specific demographic group of customer.

- Facilitated Workshops

- Brainstorming

- Nominal Group Technique: Like Brainstorming but here, they rank the most useful ideas.

- Multi-criteria Decision Analysis: stakeholders quantify requirement using decision matrix

- Mind maps.

- Affinity diagrams: sorting the requirement based in similarities. Or in categories

- Questioners and surveys

- Observation:

- Prototype

- Benchmarking.

- Context diagram: context level data flow diagram.

- Group decision making: to resolve the conflicts:

  - Dictatorship technique: there is one person to make decision for the entire group

  - Plurality technique: the decision made through the largest number of supporters.

  - Consensus approach: some group willing to accept another point.

- Delphi technique: send request to experts and compiled the response then send back again to the experts until reach agreement.

The output of collect requirement is

- Requirement Document.

- Traceability matrix: line the requirement with the objectives and other requirement and also we need to document all requirement attributes (source status….) and also who will manage it.

You need to make an acceptance criteria to ensure the requirements are met.

PM must rank requirement by order of importance and balancing requirement and resolving the conflicts and that happen after identify and priorities all requirements.

- Some time the PM can’t resolve it alone but before he needs to follow the list

  - You need to accept the best comply with

    - Business need

    - Project charter

    - Project scope statement

    - Project constrains.

Product analysis: critical tool that allows PM to make sure the product and project scope are understood and accurate.

The WBS: is effort to decompose the deliverables into smaller pieces called “Work package”

WBS work refers to the work products, Deliverable not to ACTIONS “NOUNS of THINGS not ACTIONS”

Not only customer deliverable are included in the WBS. Any deliverable are included.

Task is the smallest piece of work that make up that activity.

Often the WBS are numbered for ease location later.

Control account: tool to allow analysis the work performance data.

WBS are:

- Graphical picture of the hierarchy of the project.

- Identifies deliverable to be completed

- Foundation of the project.

- Should exist for every project

- Can be reused for other projects

- Does NOT show dependencies.

WBS Dictionary:

- output of creation WBS

- can used as a part of Work Authorizing system

- describes the schedule milestone acceptance criteria and other information related to WORK Package

Scope Baseline: is the version of WBS, WBS directory and Project scope statement that is approved at the end of planning before the project work begins.

Validate Scope: Validate Scope process, which is one of those processes, is to formally accept completed deliverables and obtain sign-off that the deliverables are satisfactory and meet stakeholders’ expectations and the documented requirements. involves planned meetings with customer or sponsor to gain the formal acceptance of deliverables.

The most important fact you should know about the Validate Scope process is that Validate Scope formalizes the acceptance of the project scope and is primarily concerned with the acceptance of project deliverables. Don’t confuse this process with the Control Quality process.

Control Quality = checking for correct work results and assuring that the quality requirements are met

Validate Scope = accepting work results

The outputs of Validate Scope are accepted deliverables, change requests, work performance information, and project documents updates. Accepted deliverables are concerned with the formal acceptance of the work by the stakeholders.

Figure in P184 is important

In Schedule management plan:

- can be formal or informal

- can specify types of report

- identify the performance measurement

In Define activities:

- It involves taking the Work Package created in WBS and decomposing them to activities that are required to produce the work package deliverables. ”is not always done as a separate process ”

- This activity should be at level small enough to estimate, schedule, monitor, control.

Milestones:

- Not a work activity

- Have no duration

- Maybe included in Project charter.

- Another name “checkpoint” to help control project

Network Diagram:

- Show dependencies

- If the activity duration estimates are added to the network diagram it show critical path.

- If there as time or calendar it called “time-scaled schedule network diagram”

Methods to draw Network diagram:

- Precedence Diagramming Method ”activity-on-node”

  - Finish-to-start

  - Start-to-start

  - Finish-to-finish

  - Start-to-finish

- Arrow Diagramming Method

- Graphic Evaluation and Review Method: computer simulation technique that allow loop between activity “often as WRONG CHOICE”

Types of dependencies:

- Mandatory dependency (Hard Logic):

- Discretionary dependency (Soft Logic, preferred or preferential) it is important if we need to fast track the project.

- Internal dependency

- External dependency

Project team identify Discretionary and Mandatory dependencies

Project Managers identify Internal and External dependencies

Leads: the activity can start before the predecessor activity completed

Lags: a waiting time inserted between activities.

When activates are sequenced the type and quantity of resources “equipment, materails, people….”are determined.

You cannot estimate activity duration unless you have determined the resource assign to this activity.

The team often estimate the time as they expert on this matter.

Padding :is extra time or cost added to an estimate because the estimater does not have enough information. If that you need to address it as a reserve in Risk management.

To estimate the expected time you can use some techniques like:

- One-Point Estimation: could be Expert judgment, historical information or just a guess.

- Analogous Estimation (Top-down): use Expert judgment, historical information

- Parametric Estimation: Relationships between variables on activity to calculate time or cost ike one hour per 10 lines of codes. There are two ways:

  - Regression analysis (scatter diagram)

  - Learning curve: the first 100 lines take more time than the next 100 lines

    - Heuristics 80/20

- Three-Point Estimation:

  - Optimistic

  - Pessimistic

  - Most likely

    - Triangular Distribution (Simple Average , Straight Average)	 	(P+O+M)/3

    - Beta Distribution (Weighted Average, PERT Average )                     	(P+4M+O)/6

    - Beta Activity Standard Deviation

(P-O)/6

- Range of the estimation =  expected time in Beta (-/+) Beta Activity Standard

(Greater range = Greater Risk)

Schedule model: consists of all the project data that will be used to calculate the schedule. The project schedule is the output of schedule model

When finishing the initial schedule model you begin schedule network analysis to create final schedule. This analysis may use one or more of these techniques:

- Critical path method

- Schedule compression

- Modeling

- Resource optimization

- Critical chain methods

Critical path: the longest path through a network diagram and determines the shortest time it could take to complete the project. It has ZERO FLOAT in Planning but in Execution it may be has negative or positive.

Float (Slack)=	Late Start – Early Start = Late Finish – Early Finish

- Total Float(Slack): the amount of time an activity can be delayed without delaying the project end date

  - Free Float+ Free Float+ Free Float= Total Float

- Free Float (Slack): the amount of time an activity can be delayed without delaying the early start of its successor.

- Project Float (Slack): the amount of time the project can be delayed without delaying the externally imposed project competition date

You need to choose the earlier late start.

After we receive the activity estimation, we must do a Schedule Compression before finalized it

If you have a negative float in critical path, you need to do a Schedule Compression:

- Fast Tracking: taking critical path activities that were planned in series and doing then in parallel. (increase risk and require more communication)

- Crashing: involves adding or adjusting resources in order to compress the schedule while remaining the original project scope.

Modeling:

- Monte Carlo analysis: use computer software to simulate outcome of project based on the Three-point estimates.it is more accurate because it simulate the actual details of the project and calculate the probability. It can help deal with “path convergence”

Resource Optimization: find a way to adjust the use of resources

- Resource Leveling:

- Resource Smoothing.

Critical Chain Method: it uses a network diagram and critical path to develop a schedule by assigning each activity to occur as late as possible to still meet the end date.

To complete the develop schedule process we need to receive the Reserve.

The project schedule can be shown with or without dependencies and it can represent as:

- Network diagram

- Milestone chart: No duration just represent the completion of activity.it good for reporting to management or customer

- Bar charts (Gantt Chart): weak planning tool not a project management plan but it effective for progress reporting and control.

Activity: used to create COST estimates.in large project it useful to estimate at Control Account

The cost management plan can be formal or informal.

Life cycle costing: looking at cost over the entire life of the product not just a project

Value analysis: find less costly way to do the same work

Return on investment :

Types of cost:

- Variable costs: like materials, suppliers…

- Fixed costs: setup services…

And it can be:

- Direct like team training

- Indirect

Reserves analysis types:

- Contingency reserves: for known risks and it approved by PM

- Management reserves: for unknown risks. Must approved by management

Some ranges:

- Rough order of magnitude estimate: usually made in initiating - 25 to +75 percent from the actual

- Budget estimate: usually made in planning - 10 to +25 percent from the actual

- Definitive Estimate: progress +/-10 percent from the actual.

The output of estimate process are:

- Activity Cost estimate

- Basis of estimates.

Cost baseline: includes the contingency reserves which represent the funds the PM has authority to manage and control

Cost budget: is cost baseline + management reserves and It represent the available company money for the project

Cost aggregation: activity cost are rolled up to work package. Work package rolled up to control account and finally to project cost.

Sanity check: after the cost baseline and cost budget are estimated the PM may compare these numbers to any technique.

The most costly is a bottom-up analysis.

It done in Monitor and control

Earned Value Measurement: it used in performance against the scope, schedule and cost baselines.

Planned value (PV): The approved budget for the work scheduled to be completed by a specified date

Earned value (EV): The value of the work actually completed by the specified date.

Actual cost (AC): The costs actually incurred for the work completed by the specified date

Budget at completion (BAC) The original forecast budget for the project.

Estimate at completion (EAC): The forecast estimate at completion the project.

Estimate to complete (ETC): The forecast of the remaining costs to be incurred on the project.

Variance at completion (VAC) The difference between what you originally thought the project was going to cost (BAC) and what you now think it is going to cost (EAC).

| Name | Formula | Purpose |
| --- | --- | --- |
| Schedule Performance Index (SPI) | SPI = EV / PV | SPI indicates weather project schedule is ahead or behind from the planned schedule date |
| Schedule Variance (SV) | SV= EV- PV | Schedule Variance indicates schedule state (ahead or behind) in terms of monetary value |
| Cost Performance Index (CPI) | CPI = EV/ AC | CPI indicates whether project is under budget or over budget |
| Cost Variance (CV) | CV= EV – AC | CV indicates whether project is under budget or over budget in terms of monetary value |
| To Complete Performance Index (TCPI) | TCPI = BAC-EV / BAC- AC | This indicates what is the target CPI project has to maintain for the remaining work in order to maintain the cost within the allocated budget |
| Estimate at Completion (EAC) | EAC = BAC / CPI | This indicates the likely cost of project going to be once project gets completed. For details please read artile on EAC. |

A lack of attention to quality means more rework or defects

Quality is degree to which the project fulfills requirement.

The low grade of something in area does not mean low quality.

Quality Control

The perform quality control (QC) process evaluates the project results (outputs, deliverables) to ensure they comply with quality standards that were defined in the quality management plan. The QC process also identifies ways to eliminate causes of unsatisfactory results and validates that approved change requests have been implemented as approved.

QC must be conducted prior to the verify scope process and the perform quality assurance (QA) process (where the project processes and results will be audited and evaluated for continuous process improvement actions).

Think of QC as the internal quality check of the products or deliverables prior to giving them to the customer or end-user.

The key outputs from QC are the “validated deliverables”

Verify Scope

The verify scope process secures formal acceptance of the completed project deliverables from the customer, end-user, or requesting party. Verifying scope includes reviewing the deliverables with the customer to ensure that they are completed satisfactorily in order to receive formal acceptance of the deliverables.

Think of verify scope as the quality check / user acceptance testing.

The key outputs from verify scope are the “accepted deliverables”.

- The project manager should recommend improvements to the performing organization’s standards, policies, and processes. Such recommendations are expected and welcomed by management.

- Quality should be considered whenever there is a change to any of the project constraints.

  - Quality should be checked before an activity or work package is completed.

  - The project manager must spend time trying to improve quality.

  - The project manager must determine metrics to be used to measure quality before the project work begins.

  - The project manager must put in place a plan for continually improving processes.

  - The project manager must make sure authorized approaches and processes are followed.

  - Some quality activities may be done by a quality assurance or quality control department.

Marginal analysis: The revenue to be received from improving quality EQUALS the incremental cost to achieve the quality. When this happen you need to stop trying to improve quality.

Continuous Improvement (Kaizen) : continuous improvement involves continuously looking for small improvement.

Just in Time : nothing in the warehouse forces attention on quality .

Differences between :

- Plan quality management: focus on defining quality for the project, the product, and project management and planning how it will achieved.

- Perform quality assurance: it is an executing process its focus is on work being done on the project and ensure the team is following what planned to produce the deliverables.

- Control quality: examine the actual deliverables produced on the project and ensure the deliverables are correct and meet planned level of quality.

In planning the quality management plan the PM must comply with external Standards such as ISO 9000

And practices (Enterprise environmental factors)

There is no reason to negatively impact project scope, time, or cost if higher quality is not required.

There are seven basic quality tools: to clarify stakeholders’ requirements and expectations.

P 302

The control limits represent the performing organization standards for quality

Specification limits: represent the customer expectation.

The project managers human resource activities re FORMAL

RAM – Responsibility Assignment Matrix : this is chart cross-references team members with the activities they are to accomplish.

RACI Chart (Responsible, accountable, consult and inform)

Types of teams:

- Dedicated: rarely seen in functional organization and PM have more control

- Part time: often in Matrix and Functional Org.

- Partnership: save cost but difficult to manage

- Virtual:

Negotiations : you can gain  resources.

Halo Effect.

Tuckman ladder model identify :

- Forming: people are brought together as a team

- Storming: There are a disagreement as people learn to work together.

- Norming: Team members begin to build good working relationships

- Performing: the team become efficient and works effectively together.

- Adjourning: project ends and team is disbanded.

Issue Log (issue register/ action item log):

Power of the PM:

- Formal (legitimate): power from the position

- Reward:

- Penalty

- Expert

- Referent: power comes from another person like you

Leadership styles: P 360

Many conflicts can be avoided

Seven sources of conflicts:

- Schedule

- Project priorities

- Resources

- Technical options

- Administrative procedures

- Cost

- Personality

Conflicts resolution techniques:

- Collaboration (Problem solving) : Win- Win

- Compromising (Reconciling) Lose-Lose

- Forcing : win-Lose

- Withdrawal(Avoidance):

- Smoothing(Accommodating) : emphasizes agreement rather than differences of opinion.

90% of PM time spend it in communication.

Communication must be efficient (Providing only the information needed) and Effective (in right format) at (right time) and should add value to project

Communication occur internally and externally to the core project team

Vertically: up and down the levels of organization.

Horizontally: among peers.

Communication type:

- Formal written

- Formal verbal

- Informal written

- Informal verbal

Noise: Factors like the receivers environment, experiences, language and culture which affect the way the receiver decode a message.

The sender (encode the message) you need to be aware to:

- Nonverbal: a significant portion of in person communication is nonverbal. A body language.

- Paralegal: pitch and tone of voice.

- Words:

Communication Methods:

- Interactive Communication: like meetings

- Push Communication: one-way stream like status report, email updates, blogs

- Pull Communication: such as the boxes in Etisalalt Edariah.

Number of communication channels = 	N (N-1) / 2              N=number of people.

Communication Blockers: use an idiomatic with someone have another culture or bad words.

Keep managing rather than reporting.

Types of reports:

- Status Report: This report describes where the project now stands regarding the performance measurement baseline,

- Progress Report A progress report describes what has been accomplished.

- Trend report: This report examines project results over time to see if performance is improving or deteriorating.

- Forecasting Report This report predicts future project status and performance.

- Variance Report: A variance report compares actual results to baselines.

- Earned Value Report: An earned value report integrates scope, cost, and schedule measures to assess project performance, using the terms described in the Cost Management chapter

- Lessons Learned Documentation Reports on performance are used as lessons learned for future projects.

Risks:

Opportunities: positive events:

Threats: negative events:

90% of the threats in the risk management process can be eliminated.

Uncertainty: lack of knowledge.

Level of risk a group are willing to accept:

- Appetites: general high definition if the acceptable level of risk

- Tolerance: is a range and it is measurable amount of acceptable range

- Thresholds is a specific point at which risk become unacceptable.

- Averse is someone who does not want to take risks.

Read P 411

Memorize the process of RISK management plan and take note they are done in sequence.

Risk breakdown Structure: is an organizational chart that can help you identify and document risk categories (Source of risk).

Types of risk:

- Business risk: risk of gain or loss

- Pure(insurable) only loss (Fire)

Some good technique in P 415

Risk register:  is where the most of the risk information is kept. It is an output of identify risks.

The Perform Qualitative risk analysis: you can’t do something for all risks and you need to analysis risks including their probability and potential impact on the project and which ones warrant a response and then create a short list.it is important for:

- Compare the risk of the project to the overall risk of other project

- Determine whether the project should continued or terminated.

Probability and impact Matrix.

Risk urgency assessment: risk move more quickly.

Watch list: risks documented in risk register for later review during Control Risks process.

The Perform Quantitative risk analysis: involves numerically analyzing the probability and impact (the amount at stake or the consequences)

Qualitative risk analysis:	should be done, subjective evaluation. The evaluation is a 5

Quantitative risk analysis:	Not required for all projects just if it worth time and money, objective, numerical evaluation. The evaluation is 3000 $

Expected Monetary Value = Probability  x Impact

For Opportunities, the Expected Monetary Value is often Positive

Whereas for Threats, the Expected Monetary Value is usually Negative.

This calculation is done through Quantitative risk analysis but it revised during risk response planning when calculating contingency reserves.

Montoe Carlo analysis (Simulation Technique): done by computer, evaluate the overall risk In the project

P 424

In risk response, planning you will find ways to reduce or eliminate threats and make opportunities.

For the remaining threats:

- Contingency plans

- Fallback plans (if the Contingency plans are not effective)

Risk Response Strategies (Risk mitigation Strategies)

- For the THREATS:

- Avoid: may involve expanding the scope. Used for high property, high risk

- Mitigate: Reduce the probability and /or impact of threat Used for high property, high risk

- Transfer (Deflect, Allocate): make another party responsible for the risk like purchasing insurance. Used for low property, low risk

- For the OPPORTUNITIES

- Exploit (The reverse of Avoid)

- Enhance (reverse of mitigate)

- Share: allocate ownership to third party (the Best Choice)

- For the BOTH

- Accept: creation of contingency plan , passive action (Workarounds ) Used for low property, low risk

In Exam you need first to determine the situation is it a threat or opportunities then pick the right strategy.

To calculate the contingency reserve for several risk we can use:

Expected Monetary Value = Probability  x Impact

BUT take note that of P 434

You need to document noncritical risk in a watch list.

The cost of reserve should return to the company.

you must Close the risk than not applicable.

The suggested change :

- If the work not begun : the change part of plan risk response

- Otherwise :the suggested change is part of control risk output of change requests.

Important P 442

Contract Can be written or verbal and typically created with external entity and there is some exchange of goods or services. The contract forms the legal relationship between entities.

Agreements: encompassed documents or communications that outline internal or external relationship and their intentions.

Contract cluld considered an agreement but the reverse is not necessary.

In the exam think as Buyer.

Centralized contracting: there is one procurement manager and its manager may handle procurement on many projects.

Decentralized contracting: a procurement manager is assigned to one project full time and reports directly to PM.

Make or Buy analysis: is depending in calculation.

Types of Procurement Statement of Work

- Performance: describe what the final product be able to accomplish (120Km in 4s)

- Functional: the end purpose or result car with five doors

- Design: used commonly in constructions and equipment

Contracts types:

- Fixed Price (Lump sum, Firm fixed price): it is not always the best

  - Fixed price incentive fee.(90$ but every month early 10$ paid)

  - Fixed price award fee.(90$ but every month exceeds 15 will paid 5$)

  - Fixed price Economic Price adjustment (90$ but increase will allowed second year depends on …)

  - Purchase order

- Time and Material (unit price): pay per hour or per item typically simpler to allow for quick negotiation and for work to begin sooner. No matter how  productivity and have no incentive to work done quickly or efficiently. Used for small dollar amount the buyer usually used “Not To Exceed” to make sure the cost not become high. And the buyer has medium amount of risk.

- Cost reimbursable: The scope is uncertain ,the buyer have the most risk as the total cost is unknown, there is an estimate but it is not binding: and it is less costly than fixed.

  - Cost contract: cost for work no profit.

  - Cost Plus Fee (cost plus percentage of costs): Not allowed in US as it is raise the cost as the percentage will raised. Need the buyer to control & monitor.

  - Cost Plus Fixed Price: cost + a fee of 10$

  - Cost Plus incentive fee the buyer and seller share the savings or overruns.

  - Cost Plus award fee  based on performance.

Cost is made when work is completed.

Price : amount the sellers charges the buyer.

Profit :fee

Cost: how much the produce the product cost the seller.

Target price: the expected price and it is measure

Sharing ratio:  Buyer share / Seller share

Ceiling Price: the highest price the buyer will buy.

Point of Total assumption: (Ceiling Price – Target Price ) / Buyers Share ratio + Target cost.

The contract terms and conditions are most commonly created by the Buyer and it not need further legal review.

Letter of intent: is not a contract but simply a letter without legal binding

Types of noncompetitive procurements:

- Single source: preferred seller

- Solo source: only one seller.

Screening system: eliminates sellers who don’t meet the minimum requirements of the selection criteria.

Procurement manager Generally leads the Negotiations

Seller is required to deliver what in the contract even if he signed memos!!!

Stakeholder Management:

Stakeholders serves as Technical Experts.

The work cannot be done well without stakeholders involvement.

You need to:

- Identify them

- Determine their requirements

- Determine their expectations

- Determine their interests (level of engagement) improve their skills in their interests

- Determine their influence: positively or negatively

- Plan how to manage them: plan everthing

- Plan how to communicate with them

- Manage expectations, interests, influence